## Sheet4
Row Labels | remarks_value
Central Module | pending
Backend | pending
not confirm | pending
Mobile App | almost done,working,working,working,working,working,pending,pending
Apk file and Deployment | pending
creating apk file and deploy it to the play store | pending
Backend | working,working,working
button functionalities | working
client funtionality to connect with the central module | working
reciving and representing data funcionality | working
logos and animations | working
not confirm | working
UI/UX | almost done,working
creating app (as mock-up design) | working
mock-up design | almost done
User Guide | pending
creating a user guide doc for application | pending
Pump Module | pending,pending,pending,pending,pending,pending,pending
Backend | pending,pending,pending,pending,pending
Creating Relay Module conditions | pending
Creating Solonoid Valve conditions | pending
Creating water sensor conditions | pending
setup pins for water Sensor, wifi module, solonoid valve ,Relay module and led lights | pending
Wifi Module program | pending
Creating Arduino Chip | pending
not confirm | pending
Desinging 3D Module | pending
not confirm | pending
Tanky Module | pending,pending,pending,pending,pending,pending,pending,pending,pending
Backend | pending,pending,pending,pending,pending,pending,pending
Creating water level sensor conditions | pending
functionality to get the water level. | pending
functionality to send the water level to the Central Module. | pending
functionality to show the water level through Leds. | pending
setup client functionality to connect the Central Module. | pending
setup pins for level Sensor, wifi module and led light | pending
Wifi Module program | pending
Creating Arduino Chip | pending
not confirm | pending
Desinging 3D Module | pending
not confirm | pending

## Sheet1
errors/bugs
sno | Project Name: | Components: | Sub Components: | Tasks: | remarks | performer | sno | Project Name | Drawback | sno | component | bug?
| Itx Tanky | Tanky Module | Backend | setup pins for level Sensor, wifi module and led light | almost done | Hassam | 1 | Itx-tanky | wifi dependent | 1 | app | error activity UI issue ,when disconnect.
| Itx Tanky | Tanky Module | Backend | functionality to get the water level. | almost done | Hassam | 2 | Itx-tanky | too much config
| Itx Tanky | Tanky Module | Backend | functionality to send the water level to the Central Module. | almost done | Hassam
| Itx Tanky | Tanky Module | Backend | setup client functionality to connect the Central Module. | almost done | Hassam
| Itx Tanky | Tanky Module | Backend | Creating water level sensor conditions | almost done | Hassam
| Itx Tanky | Tanky Module | Backend | Wifi Module program | almost done | Hassam
| Itx Tanky | Tanky Module | Creating Arduino Chip | not confirm | pending | Haroon
| Itx Tanky | Tanky Module | Desinging 3D Module | not confirm | pending | Najam
| Itx Tanky | Mobile App | UI/UX | mock-up design | almost done | Hassam
| Itx Tanky | Mobile App | UI/UX | creating app (as mock-up design) | almost done | Hassam
| Itx Tanky | Mobile App | logos and animations | not confirm | almost done | Najam
| Itx Tanky | Mobile App | Backend | client funtionality to connect with the central module | almost done | Hassam
| Itx Tanky | Mobile App | Backend | reciving and representing data funcionality | almost done | Hassam
| Itx Tanky | Mobile App | Backend | button functionalities | almost done | Hassam
| Itx Tanky | Mobile App | User Guide | creating a user guide doc for application | pending | Hassam
| Itx Tanky | Mobile App | Apk file and Deployment | creating apk file and deploy it to the play store | pending | Hassam
| Itx Tanky | Pump Module | Backend | setup pins for water Sensor, wifi module, solonoid valve ,Relay and led lights | almost done | Hassam
| Itx Tanky | Pump Module | Backend | Creating water sensor conditions | almost done | Hassam
| Itx Tanky | Pump Module | Backend | Creating Solonoid Valve conditions | almost done | Hassam
| Itx Tanky | Pump Module | Backend | Wifi Module program | almost done | Hassam
| Itx Tanky | Pump Module | Backend | Creating Relay conditions | almost done | Hassam
| Itx Tanky | Pump Module | Desinging 3D Module | not confirm | pending | Najam
| Itx Tanky | Pump Module | Creating Arduino Chip | not confirm | pending | Haroon
| Itx Tanky | Central Module | websocket server | creating websocket server | almost done | Hassam
| Itx Tanky | Central Module | websocket server | creating module classes and its functionality and testing | almost done | Hassam
| Itx Tanky | Central Module | database | creating models in django | almost done | Hassam
| Itx Tanky | Central Module | database | creating conditions for database table updation | almost done | Hassam
| Itx Tanky | Central Module | calculation | computing data to get life time of water | almost done | Hassam
| Itx Tanky | Central Module | websocket server | functionality testing | pending | Hassam
| Itx Tanky | Pump Module | Safety condition | when pump module disconnect , pump and valve off | almost done | Hassam
| Itx Tanky | Central Module | Safety condition | when tank module disconnect ,off command to pump module . | pending | Hassam
75
35